## Testing Activity Tracker
HEALTHCONNECT CLINIC EXPERIENCE LAB - TESTING ACTIVITY TRACKER (WEEK 7)
Project Manager: Leonel Devinci Ebaha Djoki ¦ Phase: Testing, Refinement & End-to-End Validation
Test ID | Track | Component Tested | Test Objective | Expected Result | Actual Result | Result | Issue ID | Action Taken | Retest Result | Evidence
T-W7-01 | Data Analytics | KPI calculations and dashboard | Validate KPI accuracy against source dataset; verify dashboard filters | KPIs match underlying data; filters return correct values | All 3 KPIs verified; one rounding discrepancy on distance bracket filter identified | Pass | ISS-05 | Rounding corrected by DA | Dashboard retested, confirmed accurate | Updated dashboard file
T-W7-02 | Data Science | Candidate model (post Week 6 feature engineering) | Test model on held-out test set; assess impact of DEC-01/DEC-02 on performance | Performance stable or improved vs Week 5 baseline despite 2 features removed | Performance globally stable; slight recall decrease on patients with no prior history | Pass (with reservation) | ISS-04 | Accepted as documented trade-off (DEC-05); no new feature cycle | Not required (limitation accepted) | Model metrics, Decision Log DEC-05
T-W7-03 | ML Engineering | Integrated pipeline (raw data to output) | Run pipeline end to end; verify output consistency with direct model testing | Pipeline produces expected output format and values | Pipeline ran successfully; output consistent with DS model testing | Pass | None | No action needed | Confirmed ready for Week 8 | Pipeline execution log
T-W7-04 | Generative AI | AI assistant (responses, compliance, escalation) | Test consistency, KB compliance, escalation triggers, unsupported requests | Responses accurate, in scope, escalation correct, unsupported handled | One ambiguous response on rescheduling edge case; all other tests passed | Pass | ISS-06 | Prompt refined for rescheduling scenario | Retested, confirmed clear | Test case log, before/after prompt