## Updated Timeline W7
HEALTHCONNECT CLINIC EXPERIENCE LAB - UPDATED TIMELINE (WEEK 7)
Project Manager: Leonel Devinci Ebaha Djoki ¦ Updated: Week 7
WBS Code | Phase / Task | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Status
1.1 | Problem Understanding | [5 empty] | Complete
1.2 | Analysis and Solution Design | [5 empty] | Complete
1.3 | Integration, Advanced Development & Validation | [5 empty] | Complete
1.3.1 | Workstream Integration Map | [5 empty] | Complete
1.3.2 | Cross-track integration activities | [5 empty] | Complete
1.3.3 | Update risk, dependency and decision registers | [5 empty] | Complete
1.4 | Testing, Refinement & End-to-End Validation | [5 empty] | In Progress
1.4.1 | Coordinate testing across all tracks | [5 empty] | In Progress
1.4.2 | Maintain Integration & Issue Log | [5 empty] | In Progress
1.4.3 | Produce Week 8 Readiness Assessment | [5 empty] | In Progress
1.4.4 | Produce Week 7 Project Summary | [5 empty] | In Progress
1.5 | Final Integration and Presentation | [5 empty] | Planned
1.5.1 | Consolidate all track contributions | [5 empty] | Planned
1.5.2 | Coordinate final presentation | [5 empty] | Planned
1.5.3 | Produce project closeout summary | [5 empty] | Planned
Legend
Complete (Weeks 4-6)
In Progress (Week 7)
Planned (Week 8, confirmed)